## Final Dataset
assignment_id | source_task_id | student_id | student_name | assignment_title | priority | difficulty | assignment_date | start_date | due_date | completed_date | status | hours_to_start | submitted_on_time | early_start | start_group | completion_time_days | days_vs_deadline | days_before_deadline
1 | 1 | 1 | Dalila Ku | Diseñar esquema de base de datos | critical | very_hard | 2026-05-01 | 2026-05-03 23:00 | 2026-05-13 | 2026-05-14 | done | 71 | FALSE | FALSE | Late start (> 24 hours) | 13 | 1 | -1
2 | 2 | 2 | Esaú Palomo | Implementar autenticación JWT | critical | hard | 2026-05-01 | 2026-05-01 17:00 | 2026-05-18 | 2026-05-24 | done | 17 | FALSE | TRUE | Early start (<= 24 hours) | 23 | 6 | -6
3 | 3 | 3 | Yeimy Piste | Diseñar endpoints REST de la API | high | hard | 2026-05-05 | 2026-05-07 13:00 | 2026-05-12 | 2026-05-16 | done | 61 | FALSE | FALSE | Late start (> 24 hours) | 11 | 4 | -4
4 | 4 | 4 | Gael Lara | Generar script de datos de prueba | high | medium | 2026-05-05 | 2026-05-07 03:00 | 2026-05-16 | 2026-05-22 | done | 51 | FALSE | FALSE | Late start (> 24 hours) | 17 | 6 | -6
5 | 5 | 5 | Ingrid Castillo | Configurar entorno de despliegue | high | very_hard | 2026-05-10 | 2026-05-10 11:00 | 2026-05-18 | 2026-05-15 | done | 11 | TRUE | TRUE | Early start (<= 24 hours) | 5 | -3 | 3
6 | 6 | 1 | Dalila Ku | Crear formularios HTML del frontend | medium | medium | 2026-05-10 | 2026-05-11 05:00 | 2026-05-17 | 2026-05-23 | done | 29 | FALSE | FALSE | Late start (> 24 hours) | 13 | 6 | -6
7 | 7 | 2 | Esaú Palomo | Actualizar README con instrucciones | medium | easy | 2026-05-15 | 2026-05-15 02:00 | 2026-06-05 | 2026-06-10 | done | 2 | FALSE | TRUE | Early start (<= 24 hours) | 26 | 5 | -5
8 | 8 | 3 | Yeimy Piste | Agregar comentarios al código SQL | low | easy | 2026-05-15 | 2026-05-15 18:00 | 2026-05-28 | 2026-05-28 | done | 18 | TRUE | TRUE | Early start (<= 24 hours) | 13 | 0 | 0
9 | 9 | 4 | Gael Lara | Pruebas de integración de la API | medium | hard | 2026-05-20 | 2026-05-20 18:00 | 2026-06-05 | 2026-06-04 | done | 18 | TRUE | TRUE | Early start (<= 24 hours) | 15 | -1 | 1
10 | 10 | 5 | Ingrid Castillo | Documentar modelo entidad-relación | low | medium | 2026-05-25 | 2026-05-25 23:00 | 2026-05-31 | 2026-05-30 | done | 23 | TRUE | TRUE | Early start (<= 24 hours) | 5 | -1 | 1
11 | 11 | 1 | Dalila Ku | Corregir error en llave foránea de tasks | critical | hard | 2026-06-01 | 2026-06-01 11:00 | 2026-06-08 | 2026-06-07 | done | 11 | TRUE | TRUE | Early start (<= 24 hours) | 6 | -1 | 1
12 | 12 | 2 | Esaú Palomo | Migrar datos a formato CSV y JSON | high | very_hard | 2026-06-01 | 2026-06-02 17:00 | 2026-06-08 | 2026-06-14 | done | 41 | FALSE | FALSE | Late start (> 24 hours) | 13 | 6 | -6
13 | 13 | 3 | Yeimy Piste | Revisar ortografía en documentación | low | easy | 2026-06-05 | 2026-06-06 07:00 | 2026-06-15 | 2026-06-19 | done | 31 | FALSE | FALSE | Late start (> 24 hours) | 14 | 4 | -4
14 | 14 | 4 | Gael Lara | Subir archivos de datos al repositorio | medium | easy | 2026-06-10 | 2026-06-10 19:00 | 2026-06-19 | 2026-06-17 | done | 19 | TRUE | TRUE | Early start (<= 24 hours) | 7 | -2 | 2
15 | 15 | 5 | Ingrid Castillo | Optimizar consultas SQL con índices | high | hard | 2026-06-15 | 2026-06-15 20:00 | 2026-06-23 | 2026-06-20 | done | 20 | TRUE | TRUE | Early start (<= 24 hours) | 5 | -3 | 3
16 | 16 | 1 | Dalila Ku | Implementar sistema de notificaciones | low | very_hard | 2026-06-15 | 2026-06-18 08:00 | 2026-06-24 | 2026-06-30 | done | 80 | FALSE | FALSE | Late start (> 24 hours) | 15 | 6 | -6
17 | 17 | 2 | Esaú Palomo | Revisión final del skeleton antes de entrega | critical | medium | 2026-06-18 | 2026-06-18 12:00 | 2026-07-02 | 2026-07-02 | done | 12 | TRUE | TRUE | Early start (<= 24 hours) | 14 | 0 | 0
18 | 18 | 3 | Yeimy Piste | Diseñar flujo de autenticación de usuarios | medium | hard | 2026-06-10 | 2026-06-11 09:00 | 2026-06-29 | 2026-07-03 | done | 33 | FALSE | FALSE | Late start (> 24 hours) | 23 | 4 | -4
19 | 19 | 4 | Gael Lara | Crear presentación del avance al equipo | high | easy | 2026-06-20 | 2026-06-22 17:00 | 2026-07-05 | 2026-07-06 | done | 65 | FALSE | FALSE | Late start (> 24 hours) | 16 | 1 | -1
20 | 20 | 5 | Ingrid Castillo | Configurar GitHub Actions para deploy automático | critical | very_hard | 2026-06-20 | 2026-06-20 13:00 | 2026-06-30 | 2026-06-29 | done | 13 | TRUE | TRUE | Early start (<= 24 hours) | 9 | -1 | 1
21 | 1 | 1 | Dalila Ku | Diseñar esquema de base de datos | critical | very_hard | 2026-05-02 | 2026-05-02 07:00 | 2026-05-13 | 2026-05-14 | done | 7 | FALSE | TRUE | Early start (<= 24 hours) | 12 | 1 | -1
22 | 2 | 2 | Esaú Palomo | Implementar autenticación JWT | critical | hard | 2026-05-02 | 2026-05-02 06:00 | 2026-05-22 | 2026-05-21 | done | 6 | TRUE | TRUE | Early start (<= 24 hours) | 19 | -1 | 1
23 | 3 | 3 | Yeimy Piste | Diseñar endpoints REST de la API | high | hard | 2026-05-06 | 2026-05-07 09:00 | 2026-05-20 | 2026-05-27 | done | 33 | FALSE | FALSE | Late start (> 24 hours) | 21 | 7 | -7
24 | 4 | 4 | Gael Lara | Generar script de datos de prueba | high | medium | 2026-05-06 | 2026-05-06 16:00 | 2026-05-16 | 2026-05-18 | done | 16 | FALSE | TRUE | Early start (<= 24 hours) | 12 | 2 | -2
25 | 5 | 5 | Ingrid Castillo | Configurar entorno de despliegue | high | very_hard | 2026-05-11 | 2026-05-11 03:00 | 2026-05-17 | 2026-05-22 | done | 3 | FALSE | TRUE | Early start (<= 24 hours) | 11 | 5 | -5
26 | 6 | 1 | Dalila Ku | Crear formularios HTML del frontend | medium | medium | 2026-05-11 | 2026-05-11 11:00 | 2026-05-31 | 2026-05-31 | done | 11 | TRUE | TRUE | Early start (<= 24 hours) | 20 | 0 | 0
27 | 7 | 2 | Esaú Palomo | Actualizar README con instrucciones | medium | easy | 2026-05-16 | 2026-05-18 12:00 | 2026-05-28 | 2026-05-28 | done | 60 | TRUE | FALSE | Late start (> 24 hours) | 12 | 0 | 0
28 | 8 | 3 | Yeimy Piste | Agregar comentarios al código SQL | low | easy | 2026-05-16 | 2026-05-17 22:00 | 2026-06-06 | 2026-06-06 | done | 46 | TRUE | FALSE | Late start (> 24 hours) | 21 | 0 | 0
29 | 9 | 4 | Gael Lara | Pruebas de integración de la API | medium | hard | 2026-05-21 | 2026-05-21 08:00 | 2026-06-11 | 2026-06-15 | done | 8 | FALSE | TRUE | Early start (<= 24 hours) | 25 | 4 | -4
30 | 10 | 5 | Ingrid Castillo | Documentar modelo entidad-relación | low | medium | 2026-05-26 | 2026-05-26 17:00 | 2026-06-04 | 2026-06-10 | done | 17 | FALSE | TRUE | Early start (<= 24 hours) | 15 | 6 | -6
31 | 11 | 1 | Dalila Ku | Corregir error en llave foránea de tasks | critical | hard | 2026-06-02 | 2026-06-05 09:00 | 2026-06-14 | 2026-06-14 | done | 81 | TRUE | FALSE | Late start (> 24 hours) | 12 | 0 | 0
32 | 12 | 2 | Esaú Palomo | Migrar datos a formato CSV y JSON | high | very_hard | 2026-06-02 | 2026-06-03 07:00 | 2026-06-18 | 2026-06-20 | done | 31 | FALSE | FALSE | Late start (> 24 hours) | 18 | 2 | -2
33 | 13 | 3 | Yeimy Piste | Revisar ortografía en documentación | low | easy | 2026-06-06 | 2026-06-06 19:00 | 2026-06-20 | 2026-06-19 | done | 19 | TRUE | TRUE | Early start (<= 24 hours) | 13 | -1 | 1
34 | 14 | 4 | Gael Lara | Subir archivos de datos al repositorio | medium | easy | 2026-06-11 | 2026-06-14 13:00 | 2026-06-27 | 2026-07-01 | done | 85 | FALSE | FALSE | Late start (> 24 hours) | 20 | 4 | -4
35 | 15 | 5 | Ingrid Castillo | Optimizar consultas SQL con índices | high | hard | 2026-06-16 | 2026-06-17 10:00 | 2026-06-30 | 2026-07-05 | done | 34 | FALSE | FALSE | Late start (> 24 hours) | 19 | 5 | -5
36 | 16 | 1 | Dalila Ku | Implementar sistema de notificaciones | low | very_hard | 2026-06-16 | 2026-06-16 02:00 | 2026-06-24 | 2026-06-23 | done | 2 | TRUE | TRUE | Early start (<= 24 hours) | 7 | -1 | 1
37 | 17 | 2 | Esaú Palomo | Revisión final del skeleton antes de entrega | critical | medium | 2026-06-19 | 2026-06-19 16:00 | 2026-06-26 | 2026-06-26 | done | 16 | TRUE | TRUE | Early start (<= 24 hours) | 7 | 0 | 0
38 | 18 | 3 | Yeimy Piste | Diseñar flujo de autenticación de usuarios | medium | hard | 2026-06-11 | 2026-06-11 14:00 | 2026-07-02 | 2026-07-07 | done | 14 | FALSE | TRUE | Early start (<= 24 hours) | 26 | 5 | -5
39 | 19 | 4 | Gael Lara | Crear presentación del avance al equipo | high | easy | 2026-06-21 | 2026-06-21 15:00 | 2026-07-06 | 2026-07-06 | done | 15 | TRUE | TRUE | Early start (<= 24 hours) | 15 | 0 | 0
40 | 20 | 5 | Ingrid Castillo | Configurar GitHub Actions para deploy automático | critical | very_hard | 2026-06-21 | 2026-06-21 23:00 | 2026-06-27 | 2026-06-28 | done | 23 | FALSE | TRUE | Early start (<= 24 hours) | 7 | 1 | -1
41 | 1 | 1 | Dalila Ku | Diseñar esquema de base de datos | critical | very_hard | 2026-05-03 | 2026-05-03 16:00 | 2026-05-16 | 2026-05-18 | done | 16 | FALSE | TRUE | Early start (<= 24 hours) | 15 | 2 | -2
42 | 2 | 2 | Esaú Palomo | Implementar autenticación JWT | critical | hard | 2026-05-03 | 2026-05-03 14:00 | 2026-05-24 | 2026-05-23 | done | 14 | TRUE | TRUE | Early start (<= 24 hours) | 20 | -1 | 1
43 | 3 | 3 | Yeimy Piste | Diseñar endpoints REST de la API | high | hard | 2026-05-07 | 2026-05-07 20:00 | 2026-05-19 | 2026-05-18 | done | 20 | TRUE | TRUE | Early start (<= 24 hours) | 11 | -1 | 1
44 | 4 | 4 | Gael Lara | Generar script de datos de prueba | high | medium | 2026-05-07 | 2026-05-10 11:00 | 2026-05-17 | 2026-05-15 | done | 83 | TRUE | FALSE | Late start (> 24 hours) | 8 | -2 | 2
45 | 5 | 5 | Ingrid Castillo | Configurar entorno de despliegue | high | very_hard | 2026-05-12 | 2026-05-12 16:00 | 2026-05-28 | 2026-05-28 | done | 16 | TRUE | TRUE | Early start (<= 24 hours) | 16 | 0 | 0
46 | 6 | 1 | Dalila Ku | Crear formularios HTML del frontend | medium | medium | 2026-05-12 | 2026-05-14 23:00 | 2026-05-22 | 2026-05-23 | done | 71 | FALSE | FALSE | Late start (> 24 hours) | 11 | 1 | -1
47 | 7 | 2 | Esaú Palomo | Actualizar README con instrucciones | medium | easy | 2026-05-17 | 2026-05-20 22:00 | 2026-05-25 | 2026-05-25 | done | 94 | TRUE | FALSE | Late start (> 24 hours) | 8 | 0 | 0
48 | 8 | 3 | Yeimy Piste | Agregar comentarios al código SQL | low | easy | 2026-05-17 | 2026-05-17 13:00 | 2026-05-29 | 2026-06-04 | done | 13 | FALSE | TRUE | Early start (<= 24 hours) | 18 | 6 | -6
49 | 9 | 4 | Gael Lara | Pruebas de integración de la API | medium | hard | 2026-05-22 | 2026-05-22 05:00 | 2026-06-12 | 2026-06-10 | done | 5 | TRUE | TRUE | Early start (<= 24 hours) | 19 | -2 | 2
50 | 10 | 5 | Ingrid Castillo | Documentar modelo entidad-relación | low | medium | 2026-05-27 | 2026-05-27 12:00 | 2026-06-04 | 2026-06-06 | done | 12 | FALSE | TRUE | Early start (<= 24 hours) | 10 | 2 | -2
51 | 11 | 1 | Dalila Ku | Corregir error en llave foránea de tasks | critical | hard | 2026-06-03 | 2026-06-03 07:00 | 2026-06-15 | 2026-06-17 | done | 7 | FALSE | TRUE | Early start (<= 24 hours) | 14 | 2 | -2
52 | 12 | 2 | Esaú Palomo | Migrar datos a formato CSV y JSON | high | very_hard | 2026-06-03 | 2026-06-06 16:00 | 2026-06-11 | 2026-06-18 | done | 88 | FALSE | FALSE | Late start (> 24 hours) | 15 | 7 | -7
53 | 13 | 3 | Yeimy Piste | Revisar ortografía en documentación | low | easy | 2026-06-07 | 2026-06-07 11:00 | 2026-06-17 | 2026-06-16 | done | 11 | TRUE | TRUE | Early start (<= 24 hours) | 9 | -1 | 1
54 | 14 | 4 | Gael Lara | Subir archivos de datos al repositorio | medium | easy | 2026-06-12 | 2026-06-12 16:00 | 2026-06-29 | 2026-06-27 | done | 16 | TRUE | TRUE | Early start (<= 24 hours) | 15 | -2 | 2
55 | 15 | 5 | Ingrid Castillo | Optimizar consultas SQL con índices | high | hard | 2026-06-17 | 2026-06-17 01:00 | 2026-07-07 | 2026-07-07 | done | 1 | TRUE | TRUE | Early start (<= 24 hours) | 20 | 0 | 0
56 | 16 | 1 | Dalila Ku | Implementar sistema de notificaciones | low | very_hard | 2026-06-17 | 2026-06-18 09:00 | 2026-07-04 | 2026-07-04 | done | 33 | TRUE | FALSE | Late start (> 24 hours) | 17 | 0 | 0
57 | 17 | 2 | Esaú Palomo | Revisión final del skeleton antes de entrega | critical | medium | 2026-06-20 | 2026-06-23 04:00 | 2026-07-09 | 2026-07-08 | done | 76 | TRUE | FALSE | Late start (> 24 hours) | 18 | -1 | 1
58 | 18 | 3 | Yeimy Piste | Diseñar flujo de autenticación de usuarios | medium | hard | 2026-06-12 | 2026-06-13 23:00 | 2026-06-25 | 2026-06-29 | done | 47 | FALSE | FALSE | Late start (> 24 hours) | 17 | 4 | -4
59 | 19 | 4 | Gael Lara | Crear presentación del avance al equipo | high | easy | 2026-06-22 | 2026-06-22 22:00 | 2026-06-27 | 2026-06-26 | done | 22 | TRUE | TRUE | Early start (<= 24 hours) | 4 | -1 | 1
60 | 20 | 5 | Ingrid Castillo | Configurar GitHub Actions para deploy automático | critical | very_hard | 2026-06-22 | 2026-06-23 10:00 | 2026-07-02 | 2026-06-30 | done | 34 | TRUE | FALSE | Late start (> 24 hours) | 8 | -2 | 2
61 | 1 | 1 | Dalila Ku | Diseñar esquema de base de datos | critical | very_hard | 2026-05-04 | 2026-05-07 07:00 | 2026-05-18 | 2026-05-15 | done | 79 | TRUE | FALSE | Late start (> 24 hours) | 11 | -3 | 3
62 | 2 | 2 | Esaú Palomo | Implementar autenticación JWT | critical | hard | 2026-05-04 | 2026-05-07 10:00 | 2026-05-23 | 2026-05-24 | done | 82 | FALSE | FALSE | Late start (> 24 hours) | 20 | 1 | -1
63 | 3 | 3 | Yeimy Piste | Diseñar endpoints REST de la API | high | hard | 2026-05-08 | 2026-05-08 14:00 | 2026-05-28 | 2026-05-25 | done | 14 | TRUE | TRUE | Early start (<= 24 hours) | 17 | -3 | 3
64 | 4 | 4 | Gael Lara | Generar script de datos de prueba | high | medium | 2026-05-08 | 2026-05-08 07:00 | 2026-05-18 | 2026-05-15 | done | 7 | TRUE | TRUE | Early start (<= 24 hours) | 7 | -3 | 3
65 | 5 | 5 | Ingrid Castillo | Configurar entorno de despliegue | high | very_hard | 2026-05-13 | 2026-05-13 23:00 | 2026-06-02 | 2026-05-31 | done | 23 | TRUE | TRUE | Early start (<= 24 hours) | 18 | -2 | 2
66 | 6 | 1 | Dalila Ku | Crear formularios HTML del frontend | medium | medium | 2026-05-13 | 2026-05-15 16:00 | 2026-05-30 | 2026-05-30 | done | 64 | TRUE | FALSE | Late start (> 24 hours) | 17 | 0 | 0
67 | 7 | 2 | Esaú Palomo | Actualizar README con instrucciones | medium | easy | 2026-05-18 | 2026-05-18 01:00 | 2026-06-08 | 2026-06-08 | done | 1 | TRUE | TRUE | Early start (<= 24 hours) | 21 | 0 | 0
68 | 8 | 3 | Yeimy Piste | Agregar comentarios al código SQL | low | easy | 2026-05-18 | 2026-05-21 19:00 | 2026-06-02 | 2026-05-30 | done | 91 | TRUE | FALSE | Late start (> 24 hours) | 12 | -3 | 3
69 | 9 | 4 | Gael Lara | Pruebas de integración de la API | medium | hard | 2026-05-23 | 2026-05-23 16:00 | 2026-05-29 | 2026-05-31 | done | 16 | FALSE | TRUE | Early start (<= 24 hours) | 8 | 2 | -2
70 | 10 | 5 | Ingrid Castillo | Documentar modelo entidad-relación | low | medium | 2026-05-28 | 2026-05-28 19:00 | 2026-06-15 | 2026-06-13 | done | 19 | TRUE | TRUE | Early start (<= 24 hours) | 16 | -2 | 2
71 | 11 | 1 | Dalila Ku | Corregir error en llave foránea de tasks | critical | hard | 2026-06-04 | 2026-06-07 06:00 | 2026-06-19 | 2026-06-19 | done | 78 | TRUE | FALSE | Late start (> 24 hours) | 15 | 0 | 0
72 | 12 | 2 | Esaú Palomo | Migrar datos a formato CSV y JSON | high | very_hard | 2026-06-04 | 2026-06-04 09:00 | 2026-06-25 | 2026-06-22 | done | 9 | TRUE | TRUE | Early start (<= 24 hours) | 18 | -3 | 3
73 | 13 | 3 | Yeimy Piste | Revisar ortografía en documentación | low | easy | 2026-06-08 | 2026-06-08 13:00 | 2026-06-17 | 2026-06-14 | done | 13 | TRUE | TRUE | Early start (<= 24 hours) | 6 | -3 | 3
74 | 14 | 4 | Gael Lara | Subir archivos de datos al repositorio | medium | easy | 2026-06-13 | 2026-06-16 05:00 | 2026-07-02 | 2026-07-02 | done | 77 | TRUE | FALSE | Late start (> 24 hours) | 19 | 0 | 0
75 | 15 | 5 | Ingrid Castillo | Optimizar consultas SQL con índices | high | hard | 2026-06-18 | 2026-06-20 02:00 | 2026-06-25 | 2026-06-28 | done | 50 | FALSE | FALSE | Late start (> 24 hours) | 10 | 3 | -3
76 | 16 | 1 | Dalila Ku | Implementar sistema de notificaciones | low | very_hard | 2026-06-18 | 2026-06-18 08:00 | 2026-07-03 | 2026-07-05 | done | 8 | FALSE | TRUE | Early start (<= 24 hours) | 17 | 2 | -2
77 | 17 | 2 | Esaú Palomo | Revisión final del skeleton antes de entrega | critical | medium | 2026-06-21 | 2026-06-21 14:00 | 2026-06-28 | 2026-06-26 | done | 14 | TRUE | TRUE | Early start (<= 24 hours) | 5 | -2 | 2
78 | 18 | 3 | Yeimy Piste | Diseñar flujo de autenticación de usuarios | medium | hard | 2026-06-13 | 2026-06-13 01:00 | 2026-07-02 | 2026-07-02 | done | 1 | TRUE | TRUE | Early start (<= 24 hours) | 19 | 0 | 0
79 | 19 | 4 | Gael Lara | Crear presentación del avance al equipo | high | easy | 2026-06-23 | 2026-06-25 13:00 | 2026-07-09 | 2026-07-06 | done | 61 | TRUE | FALSE | Late start (> 24 hours) | 13 | -3 | 3
80 | 20 | 5 | Ingrid Castillo | Configurar GitHub Actions para deploy automático | critical | very_hard | 2026-06-23 | 2026-06-23 08:00 | 2026-07-11 | 2026-07-17 | done | 8 | FALSE | TRUE | Early start (<= 24 hours) | 24 | 6 | -6
81 | 1 | 1 | Dalila Ku | Diseñar esquema de base de datos | critical | very_hard | 2026-05-05 | 2026-05-05 12:00 | 2026-05-13 | 2026-05-13 | done | 12 | TRUE | TRUE | Early start (<= 24 hours) | 8 | 0 | 0
82 | 2 | 2 | Esaú Palomo | Implementar autenticación JWT | critical | hard | 2026-05-05 | 2026-05-06 18:00 | 2026-05-14 | 2026-05-14 | done | 42 | TRUE | FALSE | Late start (> 24 hours) | 9 | 0 | 0
83 | 3 | 3 | Yeimy Piste | Diseñar endpoints REST de la API | high | hard | 2026-05-09 | 2026-05-09 22:00 | 2026-05-22 | 2026-05-22 | done | 22 | TRUE | TRUE | Early start (<= 24 hours) | 13 | 0 | 0
84 | 4 | 4 | Gael Lara | Generar script de datos de prueba | high | medium | 2026-05-09 | 2026-05-09 20:00 | 2026-05-25 | 2026-05-26 | done | 20 | FALSE | TRUE | Early start (<= 24 hours) | 17 | 1 | -1
85 | 5 | 5 | Ingrid Castillo | Configurar entorno de despliegue | high | very_hard | 2026-05-14 | 2026-05-17 09:00 | 2026-06-03 | 2026-06-06 | done | 81 | FALSE | FALSE | Late start (> 24 hours) | 23 | 3 | -3
86 | 6 | 1 | Dalila Ku | Crear formularios HTML del frontend | medium | medium | 2026-05-14 | 2026-05-17 09:00 | 2026-05-29 | 2026-06-04 | done | 81 | FALSE | FALSE | Late start (> 24 hours) | 21 | 6 | -6
87 | 7 | 2 | Esaú Palomo | Actualizar README con instrucciones | medium | easy | 2026-05-19 | 2026-05-19 19:00 | 2026-06-02 | 2026-05-30 | done | 19 | TRUE | TRUE | Early start (<= 24 hours) | 11 | -3 | 3
88 | 8 | 3 | Yeimy Piste | Agregar comentarios al código SQL | low | easy | 2026-05-19 | 2026-05-19 20:00 | 2026-06-04 | 2026-06-02 | done | 20 | TRUE | TRUE | Early start (<= 24 hours) | 14 | -2 | 2
89 | 9 | 4 | Gael Lara | Pruebas de integración de la API | medium | hard | 2026-05-24 | 2026-05-24 02:00 | 2026-05-31 | 2026-05-31 | done | 2 | TRUE | TRUE | Early start (<= 24 hours) | 7 | 0 | 0
90 | 10 | 5 | Ingrid Castillo | Documentar modelo entidad-relación | low | medium | 2026-05-29 | 2026-05-29 10:00 | 2026-06-11 | 2026-06-10 | done | 10 | TRUE | TRUE | Early start (<= 24 hours) | 12 | -1 | 1
91 | 11 | 1 | Dalila Ku | Corregir error en llave foránea de tasks | critical | hard | 2026-06-05 | 2026-06-05 10:00 | 2026-06-16 | 2026-06-16 | done | 10 | TRUE | TRUE | Early start (<= 24 hours) | 11 | 0 | 0
92 | 12 | 2 | Esaú Palomo | Migrar datos a formato CSV y JSON | high | very_hard | 2026-06-05 | 2026-06-06 22:00 | 2026-06-24 | 2026-06-28 | done | 46 | FALSE | FALSE | Late start (> 24 hours) | 23 | 4 | -4
93 | 13 | 3 | Yeimy Piste | Revisar ortografía en documentación | low | easy | 2026-06-09 | 2026-06-09 11:00 | 2026-06-23 | 2026-06-27 | done | 11 | FALSE | TRUE | Early start (<= 24 hours) | 18 | 4 | -4
94 | 14 | 4 | Gael Lara | Subir archivos de datos al repositorio | medium | easy | 2026-06-14 | 2026-06-16 23:00 | 2026-07-02 | 2026-07-07 | done | 71 | FALSE | FALSE | Late start (> 24 hours) | 23 | 5 | -5
95 | 15 | 5 | Ingrid Castillo | Optimizar consultas SQL con índices | high | hard | 2026-06-19 | 2026-06-19 05:00 | 2026-07-06 | 2026-07-04 | done | 5 | TRUE | TRUE | Early start (<= 24 hours) | 15 | -2 | 2
96 | 16 | 1 | Dalila Ku | Implementar sistema de notificaciones | low | very_hard | 2026-06-19 | 2026-06-22 02:00 | 2026-07-10 | 2026-07-08 | done | 74 | TRUE | FALSE | Late start (> 24 hours) | 19 | -2 | 2
97 | 17 | 2 | Esaú Palomo | Revisión final del skeleton antes de entrega | critical | medium | 2026-06-22 | 2026-06-22 15:00 | 2026-07-09 | 2026-07-07 | done | 15 | TRUE | TRUE | Early start (<= 24 hours) | 15 | -2 | 2
98 | 18 | 3 | Yeimy Piste | Diseñar flujo de autenticación de usuarios | medium | hard | 2026-06-14 | 2026-06-14 22:00 | 2026-06-21 | 2026-06-27 | done | 22 | FALSE | TRUE | Early start (<= 24 hours) | 13 | 6 | -6
99 | 19 | 4 | Gael Lara | Crear presentación del avance al equipo | high | easy | 2026-06-24 | 2026-06-26 08:00 | 2026-07-12 | 2026-07-19 | done | 56 | FALSE | FALSE | Late start (> 24 hours) | 25 | 7 | -7
100 | 20 | 5 | Ingrid Castillo | Configurar GitHub Actions para deploy automático | critical | very_hard | 2026-06-24 | 2026-06-24 22:00 | 2026-06-29 | 2026-06-29 | done | 22 | TRUE | TRUE | Early start (<= 24 hours) | 5 | 0 | 0
101 | 1 | 1 | Dalila Ku | Diseñar esquema de base de datos | critical | very_hard | 2026-05-06 | 2026-05-07 12:00 | 2026-05-13 | 2026-05-14 | done | 36 | FALSE | FALSE | Late start (> 24 hours) | 8 | 1 | -1
102 | 2 | 2 | Esaú Palomo | Implementar autenticación JWT | critical | hard | 2026-05-06 | 2026-05-06 14:00 | 2026-05-23 | 2026-05-20 | done | 14 | TRUE | TRUE | Early start (<= 24 hours) | 14 | -3 | 3
103 | 3 | 3 | Yeimy Piste | Diseñar endpoints REST de la API | high | hard | 2026-05-10 | 2026-05-12 13:00 | 2026-05-23 | 2026-05-24 | done | 61 | FALSE | FALSE | Late start (> 24 hours) | 14 | 1 | -1
104 | 4 | 4 | Gael Lara | Generar script de datos de prueba | high | medium | 2026-05-10 | 2026-05-10 22:00 | 2026-05-27 | 2026-05-27 | done | 22 | TRUE | TRUE | Early start (<= 24 hours) | 17 | 0 | 0
105 | 5 | 5 | Ingrid Castillo | Configurar entorno de despliegue | high | very_hard | 2026-05-15 | 2026-05-18 04:00 | 2026-05-27 | 2026-05-29 | done | 76 | FALSE | FALSE | Late start (> 24 hours) | 14 | 2 | -2
106 | 6 | 1 | Dalila Ku | Crear formularios HTML del frontend | medium | medium | 2026-05-15 | 2026-05-15 16:00 | 2026-06-02 | 2026-06-08 | done | 16 | FALSE | TRUE | Early start (<= 24 hours) | 24 | 6 | -6
107 | 7 | 2 | Esaú Palomo | Actualizar README con instrucciones | medium | easy | 2026-05-20 | 2026-05-20 19:00 | 2026-05-31 | 2026-05-30 | done | 19 | TRUE | TRUE | Early start (<= 24 hours) | 10 | -1 | 1
108 | 8 | 3 | Yeimy Piste | Agregar comentarios al código SQL | low | easy | 2026-05-20 | 2026-05-20 04:00 | 2026-06-03 | 2026-06-07 | done | 4 | FALSE | TRUE | Early start (<= 24 hours) | 18 | 4 | -4
109 | 9 | 4 | Gael Lara | Pruebas de integración de la API | medium | hard | 2026-05-25 | 2026-05-25 03:00 | 2026-06-11 | 2026-06-08 | done | 3 | TRUE | TRUE | Early start (<= 24 hours) | 14 | -3 | 3
110 | 10 | 5 | Ingrid Castillo | Documentar modelo entidad-relación | low | medium | 2026-05-30 | 2026-06-02 19:00 | 2026-06-06 | 2026-06-05 | done | 91 | TRUE | FALSE | Late start (> 24 hours) | 6 | -1 | 1
111 | 11 | 1 | Dalila Ku | Corregir error en llave foránea de tasks | critical | hard | 2026-06-06 | 2026-06-07 01:00 | 2026-06-23 | 2026-06-26 | done | 25 | FALSE | FALSE | Late start (> 24 hours) | 20 | 3 | -3
112 | 12 | 2 | Esaú Palomo | Migrar datos a formato CSV y JSON | high | very_hard | 2026-06-06 | 2026-06-07 09:00 | 2026-06-13 | 2026-06-14 | done | 33 | FALSE | FALSE | Late start (> 24 hours) | 8 | 1 | -1
113 | 13 | 3 | Yeimy Piste | Revisar ortografía en documentación | low | easy | 2026-06-10 | 2026-06-11 03:00 | 2026-06-26 | 2026-06-26 | done | 27 | TRUE | FALSE | Late start (> 24 hours) | 16 | 0 | 0
114 | 14 | 4 | Gael Lara | Subir archivos de datos al repositorio | medium | easy | 2026-06-15 | 2026-06-17 09:00 | 2026-07-06 | 2026-07-05 | done | 57 | TRUE | FALSE | Late start (> 24 hours) | 20 | -1 | 1
115 | 15 | 5 | Ingrid Castillo | Optimizar consultas SQL con índices | high | hard | 2026-06-20 | 2026-06-20 01:00 | 2026-06-30 | 2026-07-06 | done | 1 | FALSE | TRUE | Early start (<= 24 hours) | 16 | 6 | -6
116 | 16 | 1 | Dalila Ku | Implementar sistema de notificaciones | low | very_hard | 2026-06-20 | 2026-06-20 18:00 | 2026-06-25 | 2026-07-02 | done | 18 | FALSE | TRUE | Early start (<= 24 hours) | 12 | 7 | -7
117 | 17 | 2 | Esaú Palomo | Revisión final del skeleton antes de entrega | critical | medium | 2026-06-23 | 2026-06-23 18:00 | 2026-07-12 | 2026-07-10 | done | 18 | TRUE | TRUE | Early start (<= 24 hours) | 17 | -2 | 2
118 | 18 | 3 | Yeimy Piste | Diseñar flujo de autenticación de usuarios | medium | hard | 2026-06-15 | 2026-06-18 23:00 | 2026-06-30 | 2026-07-01 | done | 95 | FALSE | FALSE | Late start (> 24 hours) | 16 | 1 | -1
119 | 19 | 4 | Gael Lara | Crear presentación del avance al equipo | high | easy | 2026-06-25 | 2026-06-28 14:00 | 2026-06-30 | 2026-06-29 | done | 86 | TRUE | FALSE | Late start (> 24 hours) | 4 | -1 | 1
120 | 20 | 5 | Ingrid Castillo | Configurar GitHub Actions para deploy automático | critical | very_hard | 2026-06-25 | 2026-06-26 11:00 | 2026-06-30 | 2026-06-27 | done | 35 | TRUE | FALSE | Late start (> 24 hours) | 2 | -3 | 3
121 | 1 | 1 | Dalila Ku | Diseñar esquema de base de datos | critical | very_hard | 2026-05-07 | 2026-05-10 17:00 | 2026-05-12 | 2026-05-12 | done | 89 | TRUE | FALSE | Late start (> 24 hours) | 5 | 0 | 0
122 | 2 | 2 | Esaú Palomo | Implementar autenticación JWT | critical | hard | 2026-05-07 | 2026-05-08 04:00 | 2026-05-28 | 2026-05-30 | done | 28 | FALSE | FALSE | Late start (> 24 hours) | 23 | 2 | -2
123 | 3 | 3 | Yeimy Piste | Diseñar endpoints REST de la API | high | hard | 2026-05-11 | 2026-05-12 18:00 | 2026-05-16 | 2026-05-23 | done | 42 | FALSE | FALSE | Late start (> 24 hours) | 12 | 7 | -7
124 | 4 | 4 | Gael Lara | Generar script de datos de prueba | high | medium | 2026-05-11 | 2026-05-14 18:00 | 2026-05-29 | 2026-06-04 | done | 90 | FALSE | FALSE | Late start (> 24 hours) | 24 | 6 | -6
125 | 5 | 5 | Ingrid Castillo | Configurar entorno de despliegue | high | very_hard | 2026-05-16 | 2026-05-16 11:00 | 2026-05-24 | 2026-05-22 | done | 11 | TRUE | TRUE | Early start (<= 24 hours) | 6 | -2 | 2
126 | 6 | 1 | Dalila Ku | Crear formularios HTML del frontend | medium | medium | 2026-05-16 | 2026-05-18 12:00 | 2026-05-22 | 2026-05-28 | done | 60 | FALSE | FALSE | Late start (> 24 hours) | 12 | 6 | -6
127 | 7 | 2 | Esaú Palomo | Actualizar README con instrucciones | medium | easy | 2026-05-21 | 2026-05-21 19:00 | 2026-06-07 | 2026-06-07 | done | 19 | TRUE | TRUE | Early start (<= 24 hours) | 17 | 0 | 0
128 | 8 | 3 | Yeimy Piste | Agregar comentarios al código SQL | low | easy | 2026-05-21 | 2026-05-22 20:00 | 2026-06-07 | 2026-06-12 | done | 44 | FALSE | FALSE | Late start (> 24 hours) | 22 | 5 | -5
129 | 9 | 4 | Gael Lara | Pruebas de integración de la API | medium | hard | 2026-05-26 | 2026-05-26 02:00 | 2026-06-10 | 2026-06-10 | done | 2 | TRUE | TRUE | Early start (<= 24 hours) | 15 | 0 | 0
130 | 10 | 5 | Ingrid Castillo | Documentar modelo entidad-relación | low | medium | 2026-05-31 | 2026-06-03 15:00 | 2026-06-11 | 2026-06-11 | done | 87 | TRUE | FALSE | Late start (> 24 hours) | 11 | 0 | 0
131 | 11 | 1 | Dalila Ku | Corregir error en llave foránea de tasks | critical | hard | 2026-06-07 | 2026-06-07 09:00 | 2026-06-28 | 2026-06-26 | done | 9 | TRUE | TRUE | Early start (<= 24 hours) | 19 | -2 | 2
132 | 12 | 2 | Esaú Palomo | Migrar datos a formato CSV y JSON | high | very_hard | 2026-06-07 | 2026-06-10 08:00 | 2026-06-19 | 2026-06-21 | done | 80 | FALSE | FALSE | Late start (> 24 hours) | 14 | 2 | -2
133 | 13 | 3 | Yeimy Piste | Revisar ortografía en documentación | low | easy | 2026-06-11 | 2026-06-13 15:00 | 2026-06-21 | 2026-06-25 | done | 63 | FALSE | FALSE | Late start (> 24 hours) | 14 | 4 | -4
134 | 14 | 4 | Gael Lara | Subir archivos de datos al repositorio | medium | easy | 2026-06-16 | 2026-06-19 02:00 | 2026-06-23 | 2026-06-25 | done | 74 | FALSE | FALSE | Late start (> 24 hours) | 9 | 2 | -2
135 | 15 | 5 | Ingrid Castillo | Optimizar consultas SQL con índices | high | hard | 2026-06-21 | 2026-06-21 16:00 | 2026-07-02 | 2026-07-02 | done | 16 | TRUE | TRUE | Early start (<= 24 hours) | 11 | 0 | 0
136 | 16 | 1 | Dalila Ku | Implementar sistema de notificaciones | low | very_hard | 2026-06-21 | 2026-06-21 03:00 | 2026-06-27 | 2026-06-26 | done | 3 | TRUE | TRUE | Early start (<= 24 hours) | 5 | -1 | 1
137 | 17 | 2 | Esaú Palomo | Revisión final del skeleton antes de entrega | critical | medium | 2026-06-24 | 2026-06-24 19:00 | 2026-07-09 | 2026-07-06 | done | 19 | TRUE | TRUE | Early start (<= 24 hours) | 12 | -3 | 3
138 | 18 | 3 | Yeimy Piste | Diseñar flujo de autenticación de usuarios | medium | hard | 2026-06-16 | 2026-06-16 10:00 | 2026-07-07 | 2026-07-05 | done | 10 | TRUE | TRUE | Early start (<= 24 hours) | 19 | -2 | 2
139 | 19 | 4 | Gael Lara | Crear presentación del avance al equipo | high | easy | 2026-06-26 | 2026-06-26 22:00 | 2026-07-01 | 2026-06-30 | done | 22 | TRUE | TRUE | Early start (<= 24 hours) | 4 | -1 | 1
140 | 20 | 5 | Ingrid Castillo | Configurar GitHub Actions para deploy automático | critical | very_hard | 2026-06-26 | 2026-06-26 11:00 | 2026-07-06 | 2026-07-04 | done | 11 | TRUE | TRUE | Early start (<= 24 hours) | 8 | -2 | 2
141 | 1 | 1 | Dalila Ku | Diseñar esquema de base de datos | critical | very_hard | 2026-05-08 | 2026-05-10 15:00 | 2026-05-24 | 2026-05-29 | done | 63 | FALSE | FALSE | Late start (> 24 hours) | 21 | 5 | -5
142 | 2 | 2 | Esaú Palomo | Implementar autenticación JWT | critical | hard | 2026-05-08 | 2026-05-09 23:00 | 2026-05-16 | 2026-05-20 | done | 47 | FALSE | FALSE | Late start (> 24 hours) | 12 | 4 | -4
143 | 3 | 3 | Yeimy Piste | Diseñar endpoints REST de la API | high | hard | 2026-05-12 | 2026-05-14 14:00 | 2026-05-23 | 2026-05-29 | done | 62 | FALSE | FALSE | Late start (> 24 hours) | 17 | 6 | -6
144 | 4 | 4 | Gael Lara | Generar script de datos de prueba | high | medium | 2026-05-12 | 2026-05-15 05:00 | 2026-05-31 | 2026-06-04 | done | 77 | FALSE | FALSE | Late start (> 24 hours) | 23 | 4 | -4
145 | 5 | 5 | Ingrid Castillo | Configurar entorno de despliegue | high | very_hard | 2026-05-17 | 2026-05-17 07:00 | 2026-06-04 | 2026-06-02 | done | 7 | TRUE | TRUE | Early start (<= 24 hours) | 16 | -2 | 2
146 | 6 | 1 | Dalila Ku | Crear formularios HTML del frontend | medium | medium | 2026-05-17 | 2026-05-17 20:00 | 2026-05-22 | 2026-05-22 | done | 20 | TRUE | TRUE | Early start (<= 24 hours) | 5 | 0 | 0
147 | 7 | 2 | Esaú Palomo | Actualizar README con instrucciones | medium | easy | 2026-05-22 | 2026-05-25 11:00 | 2026-05-27 | 2026-05-25 | done | 83 | TRUE | FALSE | Late start (> 24 hours) | 3 | -2 | 2
148 | 8 | 3 | Yeimy Piste | Agregar comentarios al código SQL | low | easy | 2026-05-22 | 2026-05-22 08:00 | 2026-05-28 | 2026-05-26 | done | 8 | TRUE | TRUE | Early start (<= 24 hours) | 4 | -2 | 2
149 | 9 | 4 | Gael Lara | Pruebas de integración de la API | medium | hard | 2026-05-27 | 2026-05-27 11:00 | 2026-06-15 | 2026-06-18 | done | 11 | FALSE | TRUE | Early start (<= 24 hours) | 22 | 3 | -3
150 | 10 | 5 | Ingrid Castillo | Documentar modelo entidad-relación | low | medium | 2026-06-01 | 2026-06-01 09:00 | 2026-06-17 | 2026-06-17 | done | 9 | TRUE | TRUE | Early start (<= 24 hours) | 16 | 0 | 0
151 | 11 | 1 | Dalila Ku | Corregir error en llave foránea de tasks | critical | hard | 2026-06-08 | 2026-06-08 12:00 | 2026-06-29 | 2026-07-03 | done | 12 | FALSE | TRUE | Early start (<= 24 hours) | 25 | 4 | -4
152 | 12 | 2 | Esaú Palomo | Migrar datos a formato CSV y JSON | high | very_hard | 2026-06-08 | 2026-06-08 18:00 | 2026-06-15 | 2026-06-13 | done | 18 | TRUE | TRUE | Early start (<= 24 hours) | 5 | -2 | 2
153 | 13 | 3 | Yeimy Piste | Revisar ortografía en documentación | low | easy | 2026-06-12 | 2026-06-12 22:00 | 2026-06-27 | 2026-06-25 | done | 22 | TRUE | TRUE | Early start (<= 24 hours) | 13 | -2 | 2
154 | 14 | 4 | Gael Lara | Subir archivos de datos al repositorio | medium | easy | 2026-06-17 | 2026-06-17 05:00 | 2026-07-04 | 2026-07-04 | done | 5 | TRUE | TRUE | Early start (<= 24 hours) | 17 | 0 | 0
155 | 15 | 5 | Ingrid Castillo | Optimizar consultas SQL con índices | high | hard | 2026-06-22 | 2026-06-25 18:00 | 2026-07-13 | 2026-07-15 | done | 90 | FALSE | FALSE | Late start (> 24 hours) | 23 | 2 | -2
156 | 16 | 1 | Dalila Ku | Implementar sistema de notificaciones | low | very_hard | 2026-06-22 | 2026-06-25 12:00 | 2026-07-05 | 2026-07-04 | done | 84 | TRUE | FALSE | Late start (> 24 hours) | 12 | -1 | 1
157 | 17 | 2 | Esaú Palomo | Revisión final del skeleton antes de entrega | critical | medium | 2026-06-25 | 2026-06-25 08:00 | 2026-07-01 | 2026-07-01 | done | 8 | TRUE | TRUE | Early start (<= 24 hours) | 6 | 0 | 0
158 | 18 | 3 | Yeimy Piste | Diseñar flujo de autenticación de usuarios | medium | hard | 2026-06-17 | 2026-06-17 10:00 | 2026-06-27 | 2026-06-27 | done | 10 | TRUE | TRUE | Early start (<= 24 hours) | 10 | 0 | 0
159 | 19 | 4 | Gael Lara | Crear presentación del avance al equipo | high | easy | 2026-06-27 | 2026-06-30 19:00 | 2026-07-02 | 2026-07-02 | done | 91 | TRUE | FALSE | Late start (> 24 hours) | 5 | 0 | 0
160 | 20 | 5 | Ingrid Castillo | Configurar GitHub Actions para deploy automático | critical | very_hard | 2026-06-27 | 2026-06-27 07:00 | 2026-07-14 | 2026-07-13 | done | 7 | TRUE | TRUE | Early start (<= 24 hours) | 16 | -1 | 1
161 | 1 | 1 | Dalila Ku | Diseñar esquema de base de datos | critical | very_hard | 2026-05-09 | 2026-05-09 07:00 | 2026-05-18 | 2026-05-24 | done | 7 | FALSE | TRUE | Early start (<= 24 hours) | 15 | 6 | -6
162 | 2 | 2 | Esaú Palomo | Implementar autenticación JWT | critical | hard | 2026-05-09 | 2026-05-11 22:00 | 2026-05-27 | 2026-06-02 | done | 70 | FALSE | FALSE | Late start (> 24 hours) | 24 | 6 | -6
163 | 3 | 3 | Yeimy Piste | Diseñar endpoints REST de la API | high | hard | 2026-05-13 | 2026-05-13 17:00 | 2026-05-24 | 2026-05-21 | done | 17 | TRUE | TRUE | Early start (<= 24 hours) | 8 | -3 | 3
164 | 4 | 4 | Gael Lara | Generar script de datos de prueba | high | medium | 2026-05-13 | 2026-05-15 01:00 | 2026-05-27 | 2026-06-02 | done | 49 | FALSE | FALSE | Late start (> 24 hours) | 20 | 6 | -6
165 | 5 | 5 | Ingrid Castillo | Configurar entorno de despliegue | high | very_hard | 2026-05-18 | 2026-05-20 03:00 | 2026-05-31 | 2026-06-03 | done | 51 | FALSE | FALSE | Late start (> 24 hours) | 16 | 3 | -3
166 | 6 | 1 | Dalila Ku | Crear formularios HTML del frontend | medium | medium | 2026-05-18 | 2026-05-20 18:00 | 2026-06-01 | 2026-05-31 | done | 66 | TRUE | FALSE | Late start (> 24 hours) | 13 | -1 | 1
167 | 7 | 2 | Esaú Palomo | Actualizar README con instrucciones | medium | easy | 2026-05-23 | 2026-05-23 12:00 | 2026-05-29 | 2026-05-26 | done | 12 | TRUE | TRUE | Early start (<= 24 hours) | 3 | -3 | 3
168 | 8 | 3 | Yeimy Piste | Agregar comentarios al código SQL | low | easy | 2026-05-23 | 2026-05-26 18:00 | 2026-05-28 | 2026-05-27 | done | 90 | TRUE | FALSE | Late start (> 24 hours) | 4 | -1 | 1
169 | 9 | 4 | Gael Lara | Pruebas de integración de la API | medium | hard | 2026-05-28 | 2026-05-28 06:00 | 2026-06-02 | 2026-06-07 | done | 6 | FALSE | TRUE | Early start (<= 24 hours) | 10 | 5 | -5
170 | 10 | 5 | Ingrid Castillo | Documentar modelo entidad-relación | low | medium | 2026-06-02 | 2026-06-02 11:00 | 2026-06-16 | 2026-06-16 | done | 11 | TRUE | TRUE | Early start (<= 24 hours) | 14 | 0 | 0
171 | 11 | 1 | Dalila Ku | Corregir error en llave foránea de tasks | critical | hard | 2026-06-09 | 2026-06-09 04:00 | 2026-06-25 | 2026-06-23 | done | 4 | TRUE | TRUE | Early start (<= 24 hours) | 14 | -2 | 2
172 | 12 | 2 | Esaú Palomo | Migrar datos a formato CSV y JSON | high | very_hard | 2026-06-09 | 2026-06-12 22:00 | 2026-06-30 | 2026-07-06 | done | 94 | FALSE | FALSE | Late start (> 24 hours) | 27 | 6 | -6
173 | 13 | 3 | Yeimy Piste | Revisar ortografía en documentación | low | easy | 2026-06-13 | 2026-06-15 13:00 | 2026-06-30 | 2026-07-05 | done | 61 | FALSE | FALSE | Late start (> 24 hours) | 22 | 5 | -5
174 | 14 | 4 | Gael Lara | Subir archivos de datos al repositorio | medium | easy | 2026-06-18 | 2026-06-21 08:00 | 2026-07-01 | 2026-06-29 | done | 80 | TRUE | FALSE | Late start (> 24 hours) | 11 | -2 | 2
175 | 15 | 5 | Ingrid Castillo | Optimizar consultas SQL con índices | high | hard | 2026-06-23 | 2026-06-23 15:00 | 2026-07-07 | 2026-07-06 | done | 15 | TRUE | TRUE | Early start (<= 24 hours) | 13 | -1 | 1
176 | 16 | 1 | Dalila Ku | Implementar sistema de notificaciones | low | very_hard | 2026-06-23 | 2026-06-26 21:00 | 2026-07-11 | 2026-07-09 | done | 93 | TRUE | FALSE | Late start (> 24 hours) | 16 | -2 | 2
177 | 17 | 2 | Esaú Palomo | Revisión final del skeleton antes de entrega | critical | medium | 2026-06-26 | 2026-06-28 22:00 | 2026-07-06 | 2026-07-05 | done | 70 | TRUE | FALSE | Late start (> 24 hours) | 9 | -1 | 1
178 | 18 | 3 | Yeimy Piste | Diseñar flujo de autenticación de usuarios | medium | hard | 2026-06-18 | 2026-06-19 03:00 | 2026-07-07 | 2026-07-14 | done | 27 | FALSE | FALSE | Late start (> 24 hours) | 26 | 7 | -7
179 | 19 | 4 | Gael Lara | Crear presentación del avance al equipo | high | easy | 2026-06-28 | 2026-06-28 08:00 | 2026-07-19 | 2026-07-19 | done | 8 | TRUE | TRUE | Early start (<= 24 hours) | 21 | 0 | 0
180 | 20 | 5 | Ingrid Castillo | Configurar GitHub Actions para deploy automático | critical | very_hard | 2026-06-28 | 2026-06-28 19:00 | 2026-07-12 | 2026-07-09 | done | 19 | TRUE | TRUE | Early start (<= 24 hours) | 11 | -3 | 3
181 | 1 | 1 | Dalila Ku | Diseñar esquema de base de datos | critical | very_hard | 2026-05-10 | 2026-05-12 08:00 | 2026-05-28 | 2026-05-28 | done | 56 | TRUE | FALSE | Late start (> 24 hours) | 18 | 0 | 0
182 | 2 | 2 | Esaú Palomo | Implementar autenticación JWT | critical | hard | 2026-05-10 | 2026-05-10 09:00 | 2026-05-30 | 2026-05-28 | done | 9 | TRUE | TRUE | Early start (<= 24 hours) | 18 | -2 | 2
183 | 3 | 3 | Yeimy Piste | Diseñar endpoints REST de la API | high | hard | 2026-05-14 | 2026-05-16 23:00 | 2026-06-01 | 2026-06-07 | done | 71 | FALSE | FALSE | Late start (> 24 hours) | 24 | 6 | -6
184 | 4 | 4 | Gael Lara | Generar script de datos de prueba | high | medium | 2026-05-14 | 2026-05-17 05:00 | 2026-06-03 | 2026-06-03 | done | 77 | TRUE | FALSE | Late start (> 24 hours) | 20 | 0 | 0
185 | 5 | 5 | Ingrid Castillo | Configurar entorno de despliegue | high | very_hard | 2026-05-19 | 2026-05-20 17:00 | 2026-06-07 | 2026-06-04 | done | 41 | TRUE | FALSE | Late start (> 24 hours) | 16 | -3 | 3
186 | 6 | 1 | Dalila Ku | Crear formularios HTML del frontend | medium | medium | 2026-05-19 | 2026-05-21 13:00 | 2026-06-05 | 2026-06-04 | done | 61 | TRUE | FALSE | Late start (> 24 hours) | 16 | -1 | 1
187 | 7 | 2 | Esaú Palomo | Actualizar README con instrucciones | medium | easy | 2026-05-24 | 2026-05-26 20:00 | 2026-06-09 | 2026-06-08 | done | 68 | TRUE | FALSE | Late start (> 24 hours) | 15 | -1 | 1
188 | 8 | 3 | Yeimy Piste | Agregar comentarios al código SQL | low | easy | 2026-05-24 | 2026-05-24 20:00 | 2026-06-13 | 2026-06-16 | done | 20 | FALSE | TRUE | Early start (<= 24 hours) | 23 | 3 | -3
189 | 9 | 4 | Gael Lara | Pruebas de integración de la API | medium | hard | 2026-05-29 | 2026-05-31 08:00 | 2026-06-09 | 2026-06-07 | done | 56 | TRUE | FALSE | Late start (> 24 hours) | 9 | -2 | 2
190 | 10 | 5 | Ingrid Castillo | Documentar modelo entidad-relación | low | medium | 2026-06-03 | 2026-06-03 21:00 | 2026-06-19 | 2026-06-18 | done | 21 | TRUE | TRUE | Early start (<= 24 hours) | 15 | -1 | 1
191 | 11 | 1 | Dalila Ku | Corregir error en llave foránea de tasks | critical | hard | 2026-06-10 | 2026-06-12 07:00 | 2026-06-28 | 2026-07-03 | done | 55 | FALSE | FALSE | Late start (> 24 hours) | 23 | 5 | -5
192 | 12 | 2 | Esaú Palomo | Migrar datos a formato CSV y JSON | high | very_hard | 2026-06-10 | 2026-06-10 07:00 | 2026-06-17 | 2026-06-15 | done | 7 | TRUE | TRUE | Early start (<= 24 hours) | 5 | -2 | 2
193 | 13 | 3 | Yeimy Piste | Revisar ortografía en documentación | low | easy | 2026-06-14 | 2026-06-17 13:00 | 2026-06-30 | 2026-07-01 | done | 85 | FALSE | FALSE | Late start (> 24 hours) | 17 | 1 | -1
194 | 14 | 4 | Gael Lara | Subir archivos de datos al repositorio | medium | easy | 2026-06-19 | 2026-06-21 04:00 | 2026-06-29 | 2026-06-29 | done | 52 | TRUE | FALSE | Late start (> 24 hours) | 10 | 0 | 0
195 | 15 | 5 | Ingrid Castillo | Optimizar consultas SQL con índices | high | hard | 2026-06-24 | 2026-06-24 02:00 | 2026-06-30 | 2026-06-28 | done | 2 | TRUE | TRUE | Early start (<= 24 hours) | 4 | -2 | 2
196 | 16 | 1 | Dalila Ku | Implementar sistema de notificaciones | low | very_hard | 2026-06-24 | 2026-06-24 01:00 | 2026-07-13 | 2026-07-12 | done | 1 | TRUE | TRUE | Early start (<= 24 hours) | 18 | -1 | 1
197 | 17 | 2 | Esaú Palomo | Revisión final del skeleton antes de entrega | critical | medium | 2026-06-27 | 2026-06-27 21:00 | 2026-07-18 | 2026-07-16 | done | 21 | TRUE | TRUE | Early start (<= 24 hours) | 19 | -2 | 2
198 | 18 | 3 | Yeimy Piste | Diseñar flujo de autenticación de usuarios | medium | hard | 2026-06-19 | 2026-06-19 13:00 | 2026-06-30 | 2026-07-02 | done | 13 | FALSE | TRUE | Early start (<= 24 hours) | 13 | 2 | -2
199 | 19 | 4 | Gael Lara | Crear presentación del avance al equipo | high | easy | 2026-06-29 | 2026-06-29 21:00 | 2026-07-19 | 2026-07-16 | done | 21 | TRUE | TRUE | Early start (<= 24 hours) | 17 | -3 | 3
200 | 20 | 5 | Ingrid Castillo | Configurar GitHub Actions para deploy automático | critical | very_hard | 2026-06-29 | 2026-07-02 05:00 | 2026-07-04 | 2026-07-07 | done | 77 | FALSE | FALSE | Late start (> 24 hours) | 8 | 3 | -3
201 | 1 | 1 | Dalila Ku | Diseñar esquema de base de datos | critical | very_hard | 2026-05-11 | 2026-05-11 07:00 | 2026-05-21 | 2026-05-20 | done | 7 | TRUE | TRUE | Early start (<= 24 hours) | 9 | -1 | 1
202 | 2 | 2 | Esaú Palomo | Implementar autenticación JWT | critical | hard | 2026-05-11 | 2026-05-11 21:00 | 2026-05-20 | 2026-05-17 | done | 21 | TRUE | TRUE | Early start (<= 24 hours) | 6 | -3 | 3
203 | 3 | 3 | Yeimy Piste | Diseñar endpoints REST de la API | high | hard | 2026-05-15 | 2026-05-17 22:00 | 2026-05-27 | 2026-06-03 | done | 70 | FALSE | FALSE | Late start (> 24 hours) | 19 | 7 | -7
204 | 4 | 4 | Gael Lara | Generar script de datos de prueba | high | medium | 2026-05-15 | 2026-05-18 23:00 | 2026-05-31 | 2026-06-07 | done | 95 | FALSE | FALSE | Late start (> 24 hours) | 23 | 7 | -7
205 | 5 | 5 | Ingrid Castillo | Configurar entorno de despliegue | high | very_hard | 2026-05-20 | 2026-05-22 10:00 | 2026-05-28 | 2026-05-31 | done | 58 | FALSE | FALSE | Late start (> 24 hours) | 11 | 3 | -3
206 | 6 | 1 | Dalila Ku | Crear formularios HTML del frontend | medium | medium | 2026-05-20 | 2026-05-21 08:00 | 2026-06-07 | 2026-06-11 | done | 32 | FALSE | FALSE | Late start (> 24 hours) | 22 | 4 | -4
207 | 7 | 2 | Esaú Palomo | Actualizar README con instrucciones | medium | easy | 2026-05-25 | 2026-05-25 04:00 | 2026-05-30 | 2026-06-05 | done | 4 | FALSE | TRUE | Early start (<= 24 hours) | 11 | 6 | -6
208 | 8 | 3 | Yeimy Piste | Agregar comentarios al código SQL | low | easy | 2026-05-25 | 2026-05-25 03:00 | 2026-06-08 | 2026-06-08 | done | 3 | TRUE | TRUE | Early start (<= 24 hours) | 14 | 0 | 0
209 | 9 | 4 | Gael Lara | Pruebas de integración de la API | medium | hard | 2026-05-30 | 2026-05-30 07:00 | 2026-06-12 | 2026-06-12 | done | 7 | TRUE | TRUE | Early start (<= 24 hours) | 13 | 0 | 0
210 | 10 | 5 | Ingrid Castillo | Documentar modelo entidad-relación | low | medium | 2026-06-04 | 2026-06-04 02:00 | 2026-06-22 | 2026-06-22 | done | 2 | TRUE | TRUE | Early start (<= 24 hours) | 18 | 0 | 0
211 | 11 | 1 | Dalila Ku | Corregir error en llave foránea de tasks | critical | hard | 2026-06-11 | 2026-06-13 08:00 | 2026-06-19 | 2026-06-18 | done | 56 | TRUE | FALSE | Late start (> 24 hours) | 7 | -1 | 1
212 | 12 | 2 | Esaú Palomo | Migrar datos a formato CSV y JSON | high | very_hard | 2026-06-11 | 2026-06-11 10:00 | 2026-06-20 | 2026-06-20 | done | 10 | TRUE | TRUE | Early start (<= 24 hours) | 9 | 0 | 0
213 | 13 | 3 | Yeimy Piste | Revisar ortografía en documentación | low | easy | 2026-06-15 | 2026-06-16 12:00 | 2026-06-20 | 2026-06-19 | done | 36 | TRUE | FALSE | Late start (> 24 hours) | 4 | -1 | 1
214 | 14 | 4 | Gael Lara | Subir archivos de datos al repositorio | medium | easy | 2026-06-20 | 2026-06-20 12:00 | 2026-07-04 | 2026-07-01 | done | 12 | TRUE | TRUE | Early start (<= 24 hours) | 11 | -3 | 3
215 | 15 | 5 | Ingrid Castillo | Optimizar consultas SQL con índices | high | hard | 2026-06-25 | 2026-06-27 14:00 | 2026-07-04 | 2026-07-02 | done | 62 | TRUE | FALSE | Late start (> 24 hours) | 7 | -2 | 2
216 | 16 | 1 | Dalila Ku | Implementar sistema de notificaciones | low | very_hard | 2026-06-25 | 2026-06-25 06:00 | 2026-07-05 | 2026-07-05 | done | 6 | TRUE | TRUE | Early start (<= 24 hours) | 10 | 0 | 0
217 | 17 | 2 | Esaú Palomo | Revisión final del skeleton antes de entrega | critical | medium | 2026-06-28 | 2026-06-28 06:00 | 2026-07-18 | 2026-07-17 | done | 6 | TRUE | TRUE | Early start (<= 24 hours) | 19 | -1 | 1
218 | 18 | 3 | Yeimy Piste | Diseñar flujo de autenticación de usuarios | medium | hard | 2026-06-20 | 2026-06-22 09:00 | 2026-07-05 | 2026-07-05 | done | 57 | TRUE | FALSE | Late start (> 24 hours) | 15 | 0 | 0
219 | 19 | 4 | Gael Lara | Crear presentación del avance al equipo | high | easy | 2026-06-30 | 2026-06-30 01:00 | 2026-07-20 | 2026-07-17 | done | 1 | TRUE | TRUE | Early start (<= 24 hours) | 17 | -3 | 3
220 | 20 | 5 | Ingrid Castillo | Configurar GitHub Actions para deploy automático | critical | very_hard | 2026-06-30 | 2026-06-30 05:00 | 2026-07-17 | 2026-07-15 | done | 5 | TRUE | TRUE | Early start (<= 24 hours) | 15 | -2 | 2
221 | 1 | 1 | Dalila Ku | Diseñar esquema de base de datos | critical | very_hard | 2026-05-12 | 2026-05-12 03:00 | 2026-05-26 | 2026-05-24 | done | 3 | TRUE | TRUE | Early start (<= 24 hours) | 12 | -2 | 2
222 | 2 | 2 | Esaú Palomo | Implementar autenticación JWT | critical | hard | 2026-05-12 | 2026-05-12 20:00 | 2026-05-26 | 2026-05-31 | done | 20 | FALSE | TRUE | Early start (<= 24 hours) | 19 | 5 | -5
223 | 3 | 3 | Yeimy Piste | Diseñar endpoints REST de la API | high | hard | 2026-05-16 | 2026-05-16 21:00 | 2026-06-03 | 2026-06-06 | done | 21 | FALSE | TRUE | Early start (<= 24 hours) | 21 | 3 | -3
224 | 4 | 4 | Gael Lara | Generar script de datos de prueba | high | medium | 2026-05-16 | 2026-05-17 19:00 | 2026-06-06 | 2026-06-04 | done | 43 | TRUE | FALSE | Late start (> 24 hours) | 19 | -2 | 2
225 | 5 | 5 | Ingrid Castillo | Configurar entorno de despliegue | high | very_hard | 2026-05-21 | 2026-05-22 06:00 | 2026-06-01 | 2026-06-03 | done | 30 | FALSE | FALSE | Late start (> 24 hours) | 13 | 2 | -2
226 | 6 | 1 | Dalila Ku | Crear formularios HTML del frontend | medium | medium | 2026-05-21 | 2026-05-22 23:00 | 2026-05-31 | 2026-06-02 | done | 47 | FALSE | FALSE | Late start (> 24 hours) | 12 | 2 | -2
227 | 7 | 2 | Esaú Palomo | Actualizar README con instrucciones | medium | easy | 2026-05-26 | 2026-05-26 15:00 | 2026-06-05 | 2026-06-02 | done | 15 | TRUE | TRUE | Early start (<= 24 hours) | 7 | -3 | 3
228 | 8 | 3 | Yeimy Piste | Agregar comentarios al código SQL | low | easy | 2026-05-26 | 2026-05-26 01:00 | 2026-06-11 | 2026-06-11 | done | 1 | TRUE | TRUE | Early start (<= 24 hours) | 16 | 0 | 0
229 | 9 | 4 | Gael Lara | Pruebas de integración de la API | medium | hard | 2026-05-31 | 2026-06-03 13:00 | 2026-06-17 | 2026-06-23 | done | 85 | FALSE | FALSE | Late start (> 24 hours) | 23 | 6 | -6
230 | 10 | 5 | Ingrid Castillo | Documentar modelo entidad-relación | low | medium | 2026-06-05 | 2026-06-06 23:00 | 2026-06-14 | 2026-06-15 | done | 47 | FALSE | FALSE | Late start (> 24 hours) | 10 | 1 | -1
231 | 11 | 1 | Dalila Ku | Corregir error en llave foránea de tasks | critical | hard | 2026-06-12 | 2026-06-12 16:00 | 2026-06-28 | 2026-06-25 | done | 16 | TRUE | TRUE | Early start (<= 24 hours) | 13 | -3 | 3
232 | 12 | 2 | Esaú Palomo | Migrar datos a formato CSV y JSON | high | very_hard | 2026-06-12 | 2026-06-14 13:00 | 2026-07-02 | 2026-07-02 | done | 61 | TRUE | FALSE | Late start (> 24 hours) | 20 | 0 | 0
233 | 13 | 3 | Yeimy Piste | Revisar ortografía en documentación | low | easy | 2026-06-16 | 2026-06-18 18:00 | 2026-06-30 | 2026-06-28 | done | 66 | TRUE | FALSE | Late start (> 24 hours) | 12 | -2 | 2
234 | 14 | 4 | Gael Lara | Subir archivos de datos al repositorio | medium | easy | 2026-06-21 | 2026-06-24 16:00 | 2026-06-28 | 2026-07-03 | done | 88 | FALSE | FALSE | Late start (> 24 hours) | 12 | 5 | -5
235 | 15 | 5 | Ingrid Castillo | Optimizar consultas SQL con índices | high | hard | 2026-06-26 | 2026-06-26 17:00 | 2026-07-01 | 2026-07-01 | done | 17 | TRUE | TRUE | Early start (<= 24 hours) | 5 | 0 | 0
236 | 16 | 1 | Dalila Ku | Implementar sistema de notificaciones | low | very_hard | 2026-06-26 | 2026-06-27 21:00 | 2026-07-04 | 2026-07-05 | done | 45 | FALSE | FALSE | Late start (> 24 hours) | 9 | 1 | -1
237 | 17 | 2 | Esaú Palomo | Revisión final del skeleton antes de entrega | critical | medium | 2026-06-29 | 2026-06-30 12:00 | 2026-07-07 | 2026-07-13 | done | 36 | FALSE | FALSE | Late start (> 24 hours) | 14 | 6 | -6
238 | 18 | 3 | Yeimy Piste | Diseñar flujo de autenticación de usuarios | medium | hard | 2026-06-21 | 2026-06-22 19:00 | 2026-07-04 | 2026-07-07 | done | 43 | FALSE | FALSE | Late start (> 24 hours) | 16 | 3 | -3
239 | 19 | 4 | Gael Lara | Crear presentación del avance al equipo | high | easy | 2026-07-01 | 2026-07-03 14:00 | 2026-07-18 | 2026-07-20 | done | 62 | FALSE | FALSE | Late start (> 24 hours) | 19 | 2 | -2
240 | 20 | 5 | Ingrid Castillo | Configurar GitHub Actions para deploy automático | critical | very_hard | 2026-07-01 | 2026-07-04 06:00 | 2026-07-21 | 2026-07-19 | done | 78 | TRUE | FALSE | Late start (> 24 hours) | 18 | -2 | 2
241 | 1 | 1 | Dalila Ku | Diseñar esquema de base de datos | critical | very_hard | 2026-05-13 | 2026-05-13 01:00 | 2026-05-31 | 2026-05-30 | done | 1 | TRUE | TRUE | Early start (<= 24 hours) | 17 | -1 | 1
242 | 2 | 2 | Esaú Palomo | Implementar autenticación JWT | critical | hard | 2026-05-13 | 2026-05-13 10:00 | 2026-05-29 | 2026-06-01 | done | 10 | FALSE | TRUE | Early start (<= 24 hours) | 19 | 3 | -3
243 | 3 | 3 | Yeimy Piste | Diseñar endpoints REST de la API | high | hard | 2026-05-17 | 2026-05-19 10:00 | 2026-05-24 | 2026-05-26 | done | 58 | FALSE | FALSE | Late start (> 24 hours) | 9 | 2 | -2
244 | 4 | 4 | Gael Lara | Generar script de datos de prueba | high | medium | 2026-05-17 | 2026-05-17 05:00 | 2026-06-07 | 2026-06-14 | done | 5 | FALSE | TRUE | Early start (<= 24 hours) | 28 | 7 | -7
245 | 5 | 5 | Ingrid Castillo | Configurar entorno de despliegue | high | very_hard | 2026-05-22 | 2026-05-22 08:00 | 2026-06-03 | 2026-06-08 | done | 8 | FALSE | TRUE | Early start (<= 24 hours) | 17 | 5 | -5
246 | 6 | 1 | Dalila Ku | Crear formularios HTML del frontend | medium | medium | 2026-05-22 | 2026-05-22 21:00 | 2026-05-28 | 2026-05-26 | done | 21 | TRUE | TRUE | Early start (<= 24 hours) | 4 | -2 | 2
247 | 7 | 2 | Esaú Palomo | Actualizar README con instrucciones | medium | easy | 2026-05-27 | 2026-05-29 14:00 | 2026-06-14 | 2026-06-18 | done | 62 | FALSE | FALSE | Late start (> 24 hours) | 22 | 4 | -4
248 | 8 | 3 | Yeimy Piste | Agregar comentarios al código SQL | low | easy | 2026-05-27 | 2026-05-28 08:00 | 2026-06-15 | 2026-06-21 | done | 32 | FALSE | FALSE | Late start (> 24 hours) | 25 | 6 | -6
249 | 9 | 4 | Gael Lara | Pruebas de integración de la API | medium | hard | 2026-06-01 | 2026-06-01 01:00 | 2026-06-09 | 2026-06-08 | done | 1 | TRUE | TRUE | Early start (<= 24 hours) | 7 | -1 | 1
250 | 10 | 5 | Ingrid Castillo | Documentar modelo entidad-relación | low | medium | 2026-06-06 | 2026-06-07 02:00 | 2026-06-24 | 2026-06-22 | done | 26 | TRUE | FALSE | Late start (> 24 hours) | 16 | -2 | 2

## Indicator
start_group | assignment_count | mean_hours_to_start | mean_on_time_submission_rate | mean_completion_time_days | mean_days_before_deadline
Early start (<= 24 hours) | 135 | 11.9111 | 0.7407 | 13.437 | -0.0815
Late start (> 24 hours) | 115 | 61.6696 | 0.4087 | 15.2261 | -1.9043

## Main Result
research_question | indicator | early_start_rate | late_start_rate | difference_early_minus_late | total_assignments | interpretation
Do students who start working on assignments within 24 hours of receiving them have a higher on-time submission rate than students who start later? | Mean on-time submission rate compared between early-start and late-start groups. | 0.7407 | 0.4087 | 0.332 | 250 | Early-start students show a higher on-time submission rate.